## Sheet1
Project Documentation | [6 empty] | Complete |  | Progress |  | Unfinished |  | Bank Holiday
Week 1
Tasks | 22/04/2024 | 23/04/2024 | 24/04/2024 | 25/04/2024 | 26/04/2024
Project Description
Team Roles
Discuss Functionality Of Project
Goal Of Project
Estimated Cost
Risk Assessment
Initial Requirements
Use of UX Laws in Project
Project Design
Week 1
Tasks | 22/04/2024 | 23/04/2024 | 24/04/2024 | 25/04/2024 | 26/04/2024
Crazy 8s
Wireframes
Low Fidelity Design
Reasons for design choices
Flowchart Design
Project Development
| Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4
Tasks | 22/04/2024 | 23/04/2024 | 24/04/2024 | 25/04/2024 | 26/04/2024 | 29/04/2024 | 30/04/2024 | 2024-01-05 | 2024-02-05 | 2024-03-05 | 2024-06-05 | 2024-07-05 | 2024-08-05 | 2024-09-05 | 2024-10-05 | 13/05/2024 | 14/05/2024 | 15/05/2024 | 16/05/2024 | 17/05/2024
Creating ERD for application | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-09-05
Creating Dummy Data | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-09-05
Implementing database system | [20 empty] | Not complete | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-09-05
Creating onsite data Interactions | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-09-05
Creating navbar header layout | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-09-05
Implementing navbar css design | [20 empty] | In Progress | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-09-05
Creating navigation links | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-09-05
Creating Footer | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-09-05
Implementing Footer css design | [20 empty] | Complete | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-09-05
Creating website body css layout | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-09-05
Creating database navbar | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-09-05
Implementing database css interaction | [20 empty] | Bank Holiday (6/5/2024) | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-09-05
Creating export/search layout/design | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-09-05
Implemented functionality to export | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-10-05
Implemented search bar functionality | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-10-05
Creating user registration for site | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-09-05
Creating user login for site | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-09-05
Applying mutable changes only for accounts | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-09-05
Apply css features to login/registration pages | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-09-05
Creating database filters | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-09-05
Adding filter use to all databases | bar: 2024-01-05 to 2024-03-05; 2024-07-05 to 2024-10-05